## Slide 1: Quantum Natural Language Processing
Kick-off Meeting
14th January 2019
ICHEC, Dublin, Ireland

## Slide 2: Agenda
Project overview
People at ICHEC and Intel
Execution plan
  Work plan and timeline
  Risk mitigation
  Dissemination strategy
  Logistics
  Action points

## Slide 3: Project overview
DisCo model
  Distributional compositional semantics
  NLP algorithm to compute meanings of two sentences and decide if their meanings match
  Incorporates grammatical structure of sentences in a language into the analysis algorithms
  “Closest vector problem” algorithm
    Determine the word/phrase out of a set of words/phrases that has the closest relation to a given word/phrase
  “CSC sentence similarity” algorithm
    Compute the meaning of sentences/phrases and perform sentence similarity calculations
Objectives
  Deploy Intel Quantum Simulator (qHiPSTER) on Kay
  Implement DisCo model algorithms on qHiPSTER
  Evaluate performance of DisCo model algorithms
    NOTE: Proposal does not include comparison with a classic HPC implementation
  Period: 14-Jan-2019 to 13-Mar-2020

## Slide 4: People at ICHEC and Intel
ICHEC
  Researchers
    Lee James O’Riordan
    Myles Doyle
    Venkatesh Kannan (PI)
  Project manager
    Peter Woods
Intel
  Jim Kenneally (Lead)
  Brian Quinn
  Fabio Baruffa

## Slide 5: Agenda
Project overview
People at ICHEC and Intel
Execution plan
  Work plan and timeline
  Risk mitigation
  Dissemination strategy
  Logistics
  Action points

## Slide 6: Work plan and timeline … (1)
Project executed through 4 tasks
  Task 1 – Resource setup and problem mapping
  Task 2 – Solution development
  Task 3 – Solution evaluation and packaging
  Task 4 – Technical report and handover
Meetings
Month | Location
M01 (Jan 2019) | Project kick-off meeting (ICHEC, Dublin, Ireland)
M01 – M14 | One meeting every 3 weeks (video conference and at Intel Ireland Campus, Leixlip, Ireland as needed)
M11 (Nov 2019) | Face-to-face meeting between ICHEC and Intel Quantum Computing team at SC 2019
M14 (Mar 2020) | Project closing meeting (Intel Ireland Campus, Leixlip, Ireland)

## Slide 7: Work plan and timeline … (2)
Task 1 – Resource setup and problem mapping (M01 – M03)
  Objective
    Install and test the Intel Quantum Simulator (qHiPSTER) on the ICHEC supercomputer (Kay)
    Define the strategy to map the quantum version of the DisCo model algorithm on the Intel Quantum Simulator.
  Deliverables
    D1.1 (M03): A report describing the abstraction of the quantum DisCo model algorithms for implementation on any quantum platform, and their mapping on qHiPSTER, along with testing and evaluation methodologies, and the representative corpora.
  Milestones
    M1.1 (M01): qHiPSTER is installed and tested on ICHEC’s Kay.
    M1.2 (M03): Abstraction and mapping of DisCo algorithms on qHiPSTER is complete.
    M1.3 (M03): Testing and evaluation methodologies are defined.
    M1.4 (M03): Representative corpora for testing are ready.

## Slide 8: Work plan and timeline … (3)
Task 2 – Solution development (M04 – M11)
  Objective
    Implement the DisCo module algorithms on qHiPSTER and perform preliminary evaluations.
  Deliverables
    D2.1 (M07): A report summarising the implementation, testing and evaluation of the “closest vector problem” algorithm using the representative corpora.
    D2.2 (M11): A technical presentation at an Intel event at SC 2019.
    D2.3 (M11): A report summarising the implementation, testing and evaluation of the “CSC sentence similarity” algorithm using the representative corpora.
  Milestones
    M2.1 (M07): Implementation of the abstract and qHiPSTER-specific code, and evaluation for the “closest vector problem” is complete.
    M2.2 (M11): Implementation of the abstract and qHiPSTER-specific code, and evaluation for the “CSC sentence similarity” algorithm is complete.

## Slide 9: Work plan and timeline … (4)
Task 3 – Solution evaluation and packaging (M12 – M14)
  Objective
    Perform extended evaluations and package the software solution along with results and documentation.
  Deliverables
    D3.1 (M14): A report describing the larger corpora, and summarising the final evaluations using the larger corpora.
    D3.2 (M14): Final version of the abstract interface code for the DisCo algorithms, with documentation.
    D3.3 (M14): Final version of the qHiPSTER-specific code for the DisCo algorithms, with documentation.
    D3.4 (M14): A technical poster and presentation for ISC 2020.
  Milestones
    M3.1 (M14): Larger corpora for final testing and evaluation is ready.
    M3.2 (M14): Final version of the DisCo algorithms implementations and evaluation is complete.

## Slide 10: Work plan and timeline … (5)
Task 4 – Technical report and handover (M14)
  Objective
    Delivery of the software solutions and results to Intel.
  Deliverables
    D4.1 (M14): A consolidation of reports from deliverables D1.1, D2.1, D2.2, D2.3, D3.1, D3.3 and final software from deliverables D3.2 and D3.3.
  Milestones
    M4.1 (M14): Consolidated reports and final software are prepared.
    M4.2 (M14): Deliverable D4.1 is published on a GitHub page under the Apache License version 2.0.

## Slide 11: Risk mitigation
Risks | Steps for management
Installation and performance issues of the Intel Quantum Simulator (qHiPSTER) on the ICHEC Kay supercomputer. | The first task in the project work plan is to install and test qHiPSTER on the ICHEC supercomputer. Reservations can be made for this project on the Kay supercomputer to achieve the desired performance. The simulator developers from Intel will also be available to assist with solving installation and configuration issues.
Issues in mapping and/or implementing the DisCo model algorithms on the programming model of qHiPSTER. | The developers of qHiPSTER will be available to provide user support during implementation of the algorithms. Also, the authors of the DisCo model at the University of Oxford may be consulted for a deeper understanding of their algorithms.
Performance of the algorithm implementations is lower than expected and thus evaluation is delayed. | The size of the corpuses targeted for the evaluations may be reduced accordingly to achieve reasonable performance to get evaluation results.
Intel support is primarily sought for troubleshooting for installing and using the qHiPSTER platform.
What is the channel for ICHEC to raise a question or issue with Intel?

## Slide 12: Dissemination strategy
Proposed
  SC 2019
  ISC 2020
Any others
  Press release
  2nd All Ireland Conference on Quantum Technologies at Maynooth University, 21-Jan-2019
  EQTC 2020 (TBC)
  Intel Technical Computing Roundtable 2020
  Talk at a quantum computing workshop at UCD (TBC), Mar-2019
  …

## Slide 13: Logistics
ICHEC-Intel periodic meetings (proposed)
  Once every 3 weeks
  Mondays 11:00 (Irish time) starting 04-Feb-2019
  Google meetings at https://meet.google.com/zvp-kmhp-pak
Hosting and delivery of code and reports
  https://git.ichec.ie/intel-qnlp/intel-qnlp/
  Currently public. Access restrictions?
Any other business?

## Slide 14: Action points
Start technical tasks for M01 (ICHEC – VK, LOR, MD)
  T1.1. Install and test the Intel Quantum Simulator (qHiPSTER) on Kay
  T1.2. Investigate the DisCo model algorithms and define their mapping strategy on qHiPSTER
Set up periodic meetings on calendar (ICHEC – VK)
  ICHEC-Intel meetings
  ICHEC-internal meetings
Upcoming milestones
  M1.1 (M01): qHiPSTER is installed and tested on ICHEC’s Kay.